## Agile Project Plan
SCRUM AGILE PROJECT PLAN
| PROJECT NAME |  | PROJECT MANAGER |  | START DATE |  | END DATE
| Automated Car Parking |  | d'Amicis P. - Mantovani L. |  | 2021-06-16 |  | 2021-11-20
| TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS
| Sprint 1 |  |  |  | 2021-06-16 | 2021-06-29 | 13 | Complete
| Feature 1 | Managment of only a Client at once | d'Amicis P. - Mantovani L. |  | 2021-06-16 | 2021-06-23 | 7 | Complete
| Feature 2 | Simulated weighsensor | d'Amicis P. - Mantovani L. |  | 2021-06-23 | 2021-06-24 | 1 | Complete
| Feature 3 | Simulated outsonar | d'Amicis P. - Mantovani L. |  | 2021-06-24 | 2021-06-29 | 5 | Complete
| Sprint 2 |  |  |  | 2021-07-01 | 2021-07-13 | 12 | Complete
| Feature 4 | Parking Area KB and its management | d'Amicis P. - Mantovani L. |  | 2021-07-01 | 2021-07-06 | 5 | Complete
| Feature 5 | Managment of more Clients at once | d'Amicis P. - Mantovani L. |  | 2021-07-06 | 2021-07-07 | 1 | Complete
| Feature 6 | Simulated thermometer and fan | d'Amicis P. - Mantovani L. |  | 2021-07-07 | 2021-07-10 | 3 | Complete
| Feature 7 | Generation of TOKENID | d'Amicis P. - Mantovani L. |  | 2021-07-10 | 2021-07-13 | 3 | Complete
| Sprint 3 |  |  |  | 2021-07-16 | 2021-08-03 | 18 | Complete
| Feature 7 | Introducing Virtual Environment | d'Amicis P. - Mantovani L. |  | 2021-07-16 | 2021-07-20 | 4 | Complete
| Feature 8 | Sending commands to virtual Trolley | d'Amicis P. - Mantovani L. |  | 2021-07-20 | 2021-07-29 | 9 | Complete
| Feature 9 | Configuration and use of the map | d'Amicis P. - Mantovani L. |  | 2021-07-29 | 2021-08-03 | 5 | Complete
| Sprint 4 |  |  |  | 2021-09-15 | 2021-11-20 | 66 | Complete
| Feature 10 | Deployment of Real sonar on RaspberryPi | d'Amicis P. - Mantovani L. |  | 2021-09-15 | 2021-09-19 | 4 | Complete
| Feature 11 | Implementation of Client GUI | d'Amicis P. - Mantovani L. |  | 2021-10-01 | 2021-10-15 | 14 | Complete
| Feature 12 | Implementation of Manager GUI | d'Amicis P. - Mantovani L. |  | 2021-10-20 | 2021-10-30 | 10 | Complete
| Feature 13 | Deployment first executable prototype | d'Amicis P. - Mantovani L. |  | 2021-11-03 | 2021-11-20 | 17 | Complete